redCat Weekly Report

17.04.2007

During this week, we have broadly revised what we have done till now, and what is left. Identifying these, we reemployed the members on the tasks to be done, and arranged the schedule accordingly. Below you will see the last version of the schedule.

Apart from these, we have continued our study on bluetooth but we couldn’t come to a point worth mentioning.

| ID | Task Name | Duration | Start | Finish | Resource Names | % Complete |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Research on microcontrollers' compatibility to XSA-3S1000 board | 1 week | February 25 | March 4 | All Members |  |
| 2 | Reviewing design report | 1 week | February 25 | March 4 | All Members | 100 |
| 3 | Web page preperation | 3 days | February 27 | March 1 | Gokhan, Dicle | 100 |
| 4 | Getting used to cvs | 5 days | February 25 | March 2 | All Members | 100 |
| 5 | Revision of bluetooth usage( AT Commands) | 4 days | March 4 | March 8 | Gokhan, Ebru | 100 |
| 6 | Pretesting of data sending from admin pc to other pc | 1 day | March 8 | March 9 | Gokhan, Ebru | 100 |
|  | CODING |  |  |  |  |  |
|  | FPGA Board |  |  |  |  |  |
|  | Investigation on gxsload | 2 weeks | March 10 | March 24 | All Members | 100 |
|  | Compilation on gxsload | 2 weeks | March 25 | April 7 | Mehmet, Ebru, Gokhan | 100 |
|  | Sending .tga file from PC's parallel port to FPGA | 1week | April 1 | April 8 | Ruslan, Mehmet, Gokhan | 100 |
|  | File conversion on board (.tga->.xes) | 1 week | March 1 | March 8 | Mehmet, Ebru | 100 |
|  | Retrieval of address and RGB value from outside to FPGA board's parallel port | 1 week | April 1 | April 8 | Ruslan, Mehmet, Gokhan | 100 |
|  | Getting vast knowledge on RAM configuration | 1 week | April 1 | April 8 | Ruslan, Gokhan | 100 |
|  | Configuration of VGA port interface | 1 week | March 1 | March 8 | Mehmet | 100 |
|  | Testing of one way data sending | 2 days | April 7 | April 8 | Gokhan, Ruslan | 100 |
|  | Retrieval of event data from RAM | 2 days | April 24 | April 26 | Mehmet, Ruslan | 0 |
|  | Conversion of event data to ICallEvent and sending it out from parallel port | 3 days | April 27 | April 30 | Mehmet, Ebru | 0 |
|  | PIC + Bluetooth |  |  |  |  |  |
|  | Circuit design | 1 week | March 6 | March 12 | Ruslan, Dicle | 100 |
|  | Study on ceng336's PIC board* | 1 week | March 13 | March 20 | Ruslan, Dicle | 100 |
|  | Practicing serial to parallel(via 7 segment display) data conversion on * | 1,5 weeks | April 13 | April 25 | Ruslan, Ebru | 40 |
|  | Actualizing the conversion on our circuit |  | April 25 |  | Ruslan, Ebru | 0 |
|  | Defining our protocol on PIC | 2 days | April 20 | April 22 | Dicle, Mehmet |  |
|  | Delivery of a routine for broadcasting the environment for bluetooth devices | 15 days | April 20 | May 05 | Ruslan, Ebru |  |
|  | PC Software |  |  |  | Gokhan, Dicle | 50 |
|  | Serial port interface on PC for image and event data transfer to FPGA board(with serial cable) | 5 days | April 24 | April 29 | Dicle, Gökhan | 30 |
|  | Serial port interface on PC for image and event data transfer to FPGA board(with bluetooth, via omiting out the serial cable) | 10 days | April 24 | May 04 | Dicle, Gökhan | 30 |
| 23 | First development snapshot demonstration | 1 day | March 18 | March 18 | All Members | 100 |
| 24 | First Release and test specifications | 1 day | May 6 | May 6 | All Members | 0 |
|  | Testing |  |  |  |  |  |
| 25 | Admin Image Send Unit Testing | 1 day | April 26 | April 27 | Gökhan, Dicle | 0 |
| 26 | Admin Configuration and Event Data Send Unit Testing | 2 days | April 28 | April 30 | Gokhan, Dicle | 0 |
| 27 | VGA Display Unit Testing | 1 day | April 30 | April 30 | Mechmet, Ebru | 0 |
| 28 | Broadcast Unit Testing | 1 day | May 1 | May 1 | Mechmet, Ruslan | 0 |
| 29 | System Integration Testing | 2 days | May 2 | May 4 | All Members | 0 |
| 30 | Whole System Testing | 2 days | May 3 | May 5 | All Members | 0 |
| 31 | Presentation Preperation | 3 days | May 28 | June 1 | All Members | 0 |
| 32 | Help/ User Manual preperation | 2 days | June 7 | June 9 | All Members | 0 |
| 33 | Final Demonstration | 1 day | June 11 | June 11 | All Members | 0 |