## Tasks Table
Task Name | Duration | Start | Finish | Responsible Staff | Relative % Weight | % Complete |  | Description
Project Management | [5 empty] | 27.5
Configuration Management Plan | 15 | 2007-02-25 | 2007-03-12 | All | 10 | 100 | 10 | Transition from the first semester's work to second semester's.
First-Development Snapshot Demo | 15 | 2007-02-25 | 2007-03-12 | All | 15 | 100 | 15 | Modular, working version of the 1st semester prototype as a snapshot
Pre-First Release Prototype | 27 | 2007-03-13 | 2007-04-09 | All | 25 | 10 | 2.5 | Network, database modules will be complete. Significant progress in other modules is necessary.
First Release | 20 | 2007-04-10 | 2007-04-30 | All | 25 | 0 | 0 | Puzzle deployment module, game engine module will be complete. Graphics module should be in a good-shape.
Final Release | 41 | 2007-05-01 | 2007-06-11 | All | 25 | 0 | 0 | AI Module implementation, all modules integration, quantitative testing and documentation will be complete.
Task Name | Duration | Start | Finish | Responsible Staff | Relative % Weight | % Complete |  | Description
Content Management | [5 empty] | 100
Web page design | 23 | 2007-02-01 | 2007-02-24 | Ömer | 30 | 100 | 30
Content preparation | 12 | 2007-02-20 | 2007-03-04 | Ömer | 30 | 100 | 30 | Description of group, work; group photo
Initial deployment of the web-page | 8 | 2007-02-24 | 2007-03-04 | Ömer | 20 | 100 | 20 | Uploading recent & old documents
Updating web-page content (weekly) | 6 | 2007-02-19 | 2007-02-25 | Ömer | 20 | 100 | 20
Task Name | Duration | Start | Finish | Responsible Staff | Relative % Weight | % Complete |  | Description
Implementation | [5 empty] | 12.325
Prototype Refinement |  |  |  |  | 5 | 75 | 3.75
Modularizing the prototype | 6 | 2007-02-26 | 2007-03-04 | All | 30 | 100 | 30
CVS Tutoring | 3 | 2007-02-26 | 2007-03-01 | All | 10 | 100 | 10
Uploading to CVS | 2 | 2007-03-02 | 2007-03-04 | Ömer | 10 | 100 | 10
Adjusting the modules | 14 | 2007-02-26 | 2007-03-12 | All | 50 | 50 | 25 | According to our design documentation
Puzzle Deployment |  |  |  |  | 15 | 12.75 | 1.9125
Puzzle Analysis | 3 | 2007-02-25 | 2007-02-28 | Süleyman, Güneş | 10 | 100 | 10 | Action, rule, item extraction from the developed puzzles
Ontology Preparation | 15 | 2007-02-28 | 2007-03-15 | Süleyman, Güneş | 10 | 20 | 2 | Upon extracted information from the puzzles
Ontology Representation | 9 | 2007-03-15 | 2007-03-24 | Süleyman, Güneş | 15 | 5 | 0.75 | Via XML, XSD,...
New Puzzle Preparation (if necessary) | 44 | 2007-02-25 | 2007-04-10 | Süleyman | 15 | 0 | 0
Module Implementation | 48 | 2007-03-13 | 2007-04-30 | Süleyman, Güneş | 50 | 0 | 0
Network Module |  |  |  |  | 15 | 18.75 | 2.8125
Client/Server side sub-module revision | 14 | 2007-02-25 | 2007-03-11 | Güneş, Ömer | 10 | 100 | 10
Message type implementation | 6 | 2007-03-05 | 2007-03-11 | Güneş, Ömer | 15 | 40 | 6 | Implementing all message types
Decoder / Encoder sub-module implementation | 6 | 2007-03-12 | 2007-03-18 | Güneş, Ömer | 20 | 10 | 2 | Adjustment of the decoder/encoder sub-module to support macro/micro event transfer
Macro Events sub-module implementation | 16 | 2007-03-12 | 2007-03-28 | Güneş, Ömer | 20 | 0 | 0 | Deals with joining the game, exiting the game, etc.
Chat sub-module implementation | 14 | 2007-02-25 | 2007-03-11 | Güneş | 15 | 5 | 0.75
Network Performance Testing | 16 | 2007-03-24 | 2007-04-09 | Ömer | 20 | 0 | 0
Database |  |  |  |  | 10 | 7.5 | 0.75
E-R Model Revision | 14 | 2007-02-25 | 2007-03-11 | All | 30 | 25 | 7.5
Db System Implementation | 13 | 2007-03-12 | 2007-03-25 | Ömer, Önder | 70 | 0 | 0 | Representing objects, items, players, rules
Graphics Module |  |  |  |  | 20 | 11.5 | 2.3
Model Acquisition | 13 | 2007-03-05 | 2007-03-18 | Süleyman, Önder | 10 | 50 | 5 | Finding models (objects, players, items, texture, etc.)
Model Development | 20 | 2007-03-05 | 2007-03-25 | Süleyman, Önder | 15 | 0 | 0 | Fine-tuning the models based on our game requirements, developing new models
Creating CEGUI | 14 | 2007-02-25 | 2007-03-11 | Süleyman | 10 | 30 | 3 | Developing game interface
Game Menus | 23 | 2007-03-05 | 2007-03-28 | Süleyman, Önder | 10 | 5 | 0.5 | Developing game menus
Animation Engine | 34 | 2007-03-05 | 2007-04-08 | Süleyman, Önder | 15 | 20 | 3 | Adjusting the animation in the game
Inventory Module | 27 | 2007-03-26 | 2007-04-22 | Süleyman, Önder | 10 | 0 | 0
Collision Detection | 27 | 2007-03-26 | 2007-04-22 | Süleyman, Önder | 5 | 0 | 0
Integration | 13 | 2007-04-23 | 2007-05-06 | Süleyman, Önder | 15 | 0 | 0
Graphics Functionality Testing | 7 | 2007-05-03 | 2007-05-10 | Süleyman, Önder | 10 | 0 | 0
Game Engine Module |  |  |  |  | 20 | 0 | 0
Action/Event Authorization Sub-module Implementation | 13 | 2007-03-12 | 2007-03-25 | Süleyman, Önder | 15 | 0 | 0 | This module authorizes the actions within the game.
Game Rules Employment Sub-module Implementation | 18 | 2007-03-12 | 2007-03-30 | Süleyman, Önder | 15 | 0 | 0 | Employs the rules (e.g. water filling -> electric shock)
Object Interaction Sub-module Implementation | 21 | 2007-04-01 | 2007-04-22 | Süleyman, Önder | 25 | 0 | 0 | Interface for action selection
Graphics – Game Engine Integration | 16 | 2007-04-14 | 2007-04-30 | Süleyman, Önder, Güneş | 25 | 0 | 0 | Make sure that the effects of the rules are visually seen during gameplay.
Single Room Demonstration and Testing | 13 | 2007-04-23 | 2007-05-06 | Süleyman, Önder | 20 | 0 | 0
Artificial Intelligence Module |  |  |  |  | 10 | 2 | 0.2
Concept Refinement | 28 | 2007-02-25 | 2007-03-25 | Önder | 20 | 10 | 2 | Enhancing the underlying AI concept
Learning & resolution Algorithm Development | 28 | 2007-02-25 | 2007-03-25 | Önder | 20 | 0 | 0
Information Sharing | 8 | 2007-03-26 | 2007-04-03 | Önder, Ömer, Güneş | 10 | 0 | 0
AI Manager Module | 40 | 2007-04-15 | 2007-05-25 | Önder, Ömer, Güneş | 40 | 0 | 0
Autonomous Behaviour Integration | 10 | 2007-05-20 | 2007-05-30 | Önder | 10 | 0 | 0
I/O Interaction |  |  |  |  | 5 | 12 | 0.6
I/O Handler Implementation | 31 | 2007-02-25 | 2007-03-28 | Ömer, Güneş | 40 | 30 | 12
I/O Handler Testing | 31 | 2007-02-25 | 2007-03-28 | Ömer, Güneş | 40 | 0 | 0
Sound Module | 20 | 2007-05-07 | 2007-05-27 | Ömer, Güneş | 20 | 0 | 0
Task Name | Duration | Start | Finish | Responsible Staff | Relative % Weight | % Complete |  | Description
Testing & SQA | [5 empty] | 0
Sample Test Scenario & Cases | 14 | 2007-04-16 | 2007-04-30 | All | 30 | 0 | 0
Integration & Alpha Testing | 29 | 2007-05-01 | 2007-05-30 | All | 40 | 0 | 0
Beta Testing | 9 | 2007-06-01 | 2007-06-10 | All, Classmates | 30 | 0 | 0
Task Name | Duration | Start | Finish | Responsible Staff | Relative % Weight | % Complete |  | Description
Documentation | [5 empty] | 0
Installation Guide | 9 | 2007-06-01 | 2007-06-10 | Güneş, Ömer | 30 | 0 | 0
User's Manual | 9 | 2007-06-01 | 2007-06-10 | Önder | 40 | 0 | 0
Help Documentation | 9 | 2007-06-01 | 2007-06-10 | Süleyman | 30 | 0 | 0